## Open points
Sr No | Description | Area | Location | Status | Target Date | Assigned to | Remarks | Comments
1 | Purchase Company 10 | NOW | USA | Under Observation | 2023-06-15 | Shraddha/Hitesh | At LIVE
2 | Purchase Company 10 | CAMS | USA | Closed | 2023-06-23 | Parevi
3 | Consumption screen Company 10 | CAMS | USA | Closed | 2023-06-23 | Parevi
4 | Purchase Posting Clarksville | QB | USA | Closed | 2023-06-15 | Shraddha | Posting done
5 | Purchase Process Clarksville | NOW | USA | Under Observation | 2023-06-23 | Shraddha/Hitesh | At LIVE
6 | Production process Clarksville | CAMS/NOW | USA | Under Testing | 2023-07-17 | Parevi/Lalit
7 | FBG COA report | NOW | IND | Closed | 2023-06-06 | Parevi | Changes done and confirmed from user.
8 | GC_ShipmentDetails | NOW | IND | Closed |  | HiteshM/Shraddha | New fields are required at Commercial Invoice
9 | PET Agglomeration waste screen | CAMS | IND | In Process | 2023-06-23 | Vrushali | Under testing
10 | Project and Zone,Location update for LNR Company 30 | CAMS | USA - Comm | Closed | 2023-09-06 | Parevi | Harsh bhai will Confirm.
11 | Product should be deducted from balance at time of Consumption | CAMS | IND | Closed |  | Vrushali | All plants
12 | Merger of Companies 20/30 Database | CAMS | USA - Comm | Under Testing | 2023-07-28 | Lalit
13 | QA entries from CAMS | CAMS | IND | Hold |  | Lalit | On hold due to high priority projects
14 | Eccount report for TDS | PBI | IND | In Process | 2023-07-20 | Usha | Understanding E-account software and its database
15 | Budget Report | PBI | IND | Entered | 2023-06-30 | Usha
16 | Budget Tracker Report (NWN) | PBI | IND | Under Observation | 2023-06-23 | Dipak | Working on issue related to joining of the data
17 | Weekly Data Report (NWN) | PBI | IND | Closed | 2023-06-23 | Dipak
18 | Order Confirmation Report | PBI | IND | Closed | 2023-06-16 | Dipak
19 | FBG Production report (Machine wise) | PBI | IND | Entered | 2023-07-07 | Dipak
20 | WVN all reports | PBI | IND | Under Testing | 2023-06-30 | Dipak | Vadan bhai is checking and confirming one by one
21 | Zone Location Field merge / available for other item types / allow containers in JSP Programm | NOW | USA - Comm | Under Observation | 2023-06-21 | Hitesh M/HItesh R | Need to discuss with Harsh
22 | Pendergrass Label Match with athens | CAMS | USA | Hold | 2023-06-06 | Parevi | On hold due to high priority projects
23 | Pendergrass GI taken wrong Primary qty.(negative qty) | CAMS | USA | Closed | 2023-05-06 | Parevi | Under Testing by IT Team
24 | Liner 18/19 Lines add in Production | CAMS | USA - Comm | Hold |  | Lalit | Done in QA working with company 20 CAMS server
25 | WLR spool update transaction taking kg in primary qty | CAMS | USA - Comm | Closed | 2023-06-06 | Harsh | Harsh bhai will Confirm.
26 | QR Code Label For India Non-woven, Woven,Fiber Business | CAMS | IND | In Process | 2023-06-30 | Vrushali
27 | PET Production : Validation CheckPoints Increasing | CAMS | IND | Closed | 2023-02-06 | Parevi | PET Production Team will confirm.
28 | vTiger <-> Power Bi Connection | vTiger | IND,USA | Under Testing | 2023-07-30 | Harsh Bhai, Parevi | Connection done vTiger and Pbi -> need to discuss with Harsh bhai.
29 | Too many ABS Submitted Jobs in Queue | NOW | USA - Comm | Closed | 2023-06-16 | Hitesh | Under Testing
30 | Some times Twice at allocation line (same roll) | NOW - JSP | USA | Under Observation
31 | E mail Sending funcionality from regular user | NOW | USA - Comm | Closed |  | Sachin
32 | receive geogrid in commerce and consume from cams | NOW/CAMS | USA - Comm | Entered |  |  | Hold
33 | Sales Return Process for Company 20 | NOW | USA - Comm | Under Testing | 2023-08-20 | Hitesh M | On QA - Also Working on Com-10 & 30
34 | Back Dated Invoice creation for Fiber Glass (company 30) | NOW | USA - Comm | Closed | 2023-06-23 | Hitesh M | Check with Mukesh/Umed
35 | Length not getting displayed in DSIShippingProvisonal/Definitive | NOW | USA - Athens | Closed | 2023-06-02 | Shraddha
36 | Fiber Glass Pallet Net WT Issue | CAMS | IND | Closed |  | Parevi
37 | BGN PAllet Tranfer Facing Error | NOW | USA | Closed |  | Parevi | In Product , Lot Counter is to Automatic generation, but it has to be manually generated. so changed that in Product Level.
38 | Business wise Waste type details in CAMS waste entry screen | CAMS/NOW | IND,USA | Closed | 2023-06-08 | Vrushali
39 | Added Itemtype & itemcode in SIOutword report | NOW | IND | Closed | 2023-06-01 | Hitesh M
40 | Added shipper in Internal Documnet (company-30) | NOW | USA | Closed | 2023-06-07 | Hitesh M
41 | check sales process for fiberglass for OrderitemOderpartner link | NOW | USA | Closed | 2023-06-12 | HiteshM/Shraddha | issue in making Sales Document
42 | Change export transaction detail type for Fiber Receving in Pendergrass, Athens | CAMS | USA | Closed |  | Parevi
43 | validation requirement at production level for reuse element cams not allow to produced | CAMS | USA | Entered
44 | Power BI reports for Commerce (GM) | PBI | USA - Comm | Hold |  | Dipak | Need confirmation from internal team USA
45 | Added confirmed Del date in Open order report | NOW | IND | Closed | 2023-06-09 | Hitesh M
46 | required Zone/Location selection in Raw Material Transfer screen | CAMS | IND | Closed | 2023-07-14 | Parevi | Changes are done, but there is new requirement from User related to the changes done.
47 | Purchase Receipt CAMs Screen in Company 30(INV,BOL,PL) | CAMS | USA | Closed | 2023-07-14 | Lalit | For Kentucky and Commerce-LNR,WLR. | Kentucky done
48 | Multi KIT concept to introduce in CoreKIT business | NOW/CAMS | IND | Under Testing | 2023-07-19 | Usha/Lalit
49 | Improvements in Glass set KIT CAMS screen | CAMS/NOW | IND | Closed | 2023-06-30 | Vrushali
50 | Pallet Gross wt in pounds pass in add. data for Fiber glass | CAMS | IND | Entered | 2023-07-28 | Vrushali
51 | Open Order for PO - Issue/Pending POs | PBI | IND | Closed | 2023-07-07 | Dipak
52 | RM Inward Report | PBI | IND | Closed | 2023-07-07 | Dipak
53 | Customer wise Sales Summary Report | PBI | IND | Closed | 2023-06-30 | Dipak
54 | Reports - GlassSetKIT- Element Labels | NOW | IND | In Process | 2023-06-30 | Vrushali
55 | Reports - GlassSetKIT- CoA | NOW | IND | Closed | 2023-06-30 | Vrushali
56 | Length check issue on Pallet making screen in CAMS | CAMS-ATH | USA - ATH | Entered
57 | Powerr Automate ,learn about make flow | Power Auto | IND | In Process
58 | Certificate of Analysis (PET) | Nodejs,ReactJs | IND | In Process | 2023-06-15 | Manish
59 | FiberGlass Label issue in Sales Cycle | NOW | USA | In Process | 2023-08-10 | Hitesh M | Working on QA - For Special Label
60 | Pendergrass - Purchase and Consumption Screen LIVE | CAMS | USA | Closed | 2023-06-28 | Parevi
61 | Copy Sales Order with Cutomer PO Number & Date for Com-10 & 30 (FBG) | NOW | USA | Entered |  | HItesh/Hitesh M | AT QA
62 | Added Net Weight Column in Receiving Summary - Com-10 | NOW | USA | Closed | 2023-07-06 | Hitesh M
63 | APN and MRN set off issue | NOW | IND | Entered |  | Shraddha
64 | Stock report Quantity check report and Periodized Balance | NOW | IND | In Process | 2023-08-04 | Shraddha
65 | loading unloading form (USA) | Nodejs,ReactJs | USA | In Process |  | Manish/Dipak | frontend and databse connection is done
66 | Inventory Tracking report for all buisnesses | PBI | IND | In Process |  | Dipak
67 | Purchase Price Tracking report for RM | PBI | IND | In Process |  | Dipak
68 | Remove Quality control process in Datatex when we transfer finished goods from India to USA | NOW | USA-KY | Entered
69 | Gross weight should be added to the additional data of container elements which we transfer through XML from India to USA Datatex | NOW | USA-KY | Entered
70 | We cannot transfer pallets created in Athens(new slitter module) using an internal document or stock transaction creator | NOW | USA-KY | Entered
71 | On the inventory reports (BalanceRolls_Pallet_XLS.rpt & BalanceRolls_FG_XLS.rpt), Micro pallets coming from India or pallets made in Athens using the new slitter module, do not show Gross Weight | NOW | USA-KY | Entered
72 | In CAMS spare consumption screen we need to add Shift also, so we can see shift wise spares consumption and cost also in Power BI | CAMS-KY | USA-KY | Entered
73 | In CAMS NOW Roll Slitting and RePrint Screen and NOW Palletizing Screen when we update roll or container then date shows no label 01/01/1980 | CAMS-KY | USA-KY | Entered
74 | In Power BI need to add Quality filter in Inventory Report so we can also check inventory quality wise | PBI | USA-KY | Entered
75 | In Power BI we need open order & Inventory Plant wise, so we know how much we need to Produce for Henderson and how much we need to order to India for Athens order | PBI | USA-KY | Entered
76 | Auto Consumption of Pallets | NOW | USA - ATH | In Process | 2023-07-28 | Dipak
77 | Multimedia attachment throught CAMS | NOW/CAMS | USA | In Process | 2023-08-15 | Lalit
78 | Sales Process of Company 30 (303) | NOW | USA | Under Testing | 2023-08-15 | Hitesh M | Testing with various scenarios
77 | Sales BOL report Company 30 | NOW | USA | In Process | 2023-08-04 | Usha/Hitesh M
78 | Sales Invoice report Company 30 | NOW | USA | In Process | 2023-08-04 | Hitesh M
79 | Auto mail process for PO India | NOW | IND | In Process | 2023-08-04 | Shraddha

## Sheet1
Status
In Process
Entered
Closed
Under Observation
Under Testing
Hold

## Sheet2
company | Plant | ItemType | Process Name | Area | Status | Comments
10 | ATHENS | SPR | Purchase Receipt CAMS screen | CAMS | Done
10 | ATHENS | PLK | Purchase Receipt CAMS screen | CAMS | Done
10 | ATHENS | GEN | Purchase Receipt CAMS screen | CAMS | Done
10 | ATHENS | SER | Purchase Receipt CAMS screen | CAMS | Done
10 | ATHENS | CAP | Purchase Receipt CAMS screen | CAMS | Done
10 | ATHENS | PKG | Purchase Receipt CAMS screen | CAMS | Done
10 | ATHENS | PKG | Consumption Screen | CAMS | Done | Pending New Changes in Live
10 | ATHENS | GEN | Consumption Screen | CAMS | Done
10 | ATHENS | SER | Consumption Screen | CAMS | Done
10 | Pendergrass | SPR | Purchase Receipt CAMS screen | CAMS | Done
10 | Pendergrass | PLK | Purchase Receipt CAMS screen | CAMS | Done
10 | Pendergrass | GEN | Purchase Receipt CAMS screen | CAMS | Done
10 | Pendergrass | SER | Purchase Receipt CAMS screen | CAMS | Done
10 | Pendergrass | CAP | Purchase Receipt CAMS screen | CAMS | Done
10 | Pendergrass | PKG | Purchase Receipt CAMS screen | CAMS | Done
10 | Pendergrass | PKG | Consumption Screen | CAMS | Done
10 | Pendergrass | GEN | Consumption Screen | CAMS | Done
10 | Pendergrass | SER | Consumption Screen | CAMS | Done
30 | Kentucky | VEL | Purchase Receipt CAMS screen | CAMS | Done
30 | Kentucky | SPR | Purchase Receipt CAMS screen | CAMS | Done
30 | Kentucky | PLK | Purchase Receipt CAMS screen | CAMS | Done
30 | Kentucky | GEN | Purchase Receipt CAMS screen | CAMS | Done
30 | Kentucky | SER | Purchase Receipt CAMS screen | CAMS | Done
30 | Kentucky | RVG | Purchase Receipt CAMS screen | CAMS | Done
30 | Kentucky | RPR | Purchase Receipt CAMS screen | CAMS | Done
30 | Kentucky | FYN | Purchase Receipt CAMS screen | CAMS | Done
30 | Kentucky | PKG | Purchase Receipt CAMS screen | CAMS | Done
30 | Kentucky | RGR | Purchase Receipt CAMS screen | CAMS | Done
30 | Kentucky | FBM | Purchase Receipt CAMS screen | CAMS | Done
30 | Kentucky | PKG | Consumption Screen | CAMS | Done
30 | Kentucky | SPR | Consumption Screen | CAMS | Done
30 | Kentucky | GEN | Consumption Screen | CAMS | Done
30 | COMLNR | SPR | Purchase Receipt CAMS screen | CAMS | Pending BOL,INVOICE,Packing list number changes
30 | COMLNR | PLK | Purchase Receipt CAMS screen | CAMS
30 | COMLNR | GEN | Purchase Receipt CAMS screen | CAMS
30 | COMLNR | SER | Purchase Receipt CAMS screen | CAMS
30 | COMLNR | MSB | Purchase Receipt CAMS screen | CAMS
30 | COMLNR | RSN | Purchase Receipt CAMS screen | CAMS
30 | COMLNR | ADT | Purchase Receipt CAMS screen | CAMS
30 | COMLNR | RPR | Purchase Receipt CAMS screen | CAMS
30 | COMLNR | PKG | Purchase Receipt CAMS screen | CAMS
30 | COMLNR | RGR | Purchase Receipt CAMS screen | CAMS
30 | COMLNR | PKG | Consumption Screen | CAMS | Done
30 | COMLNR | SPR | Consumption Screen | CAMS | Done
30 | COMLNR | GEN | Consumption Screen | CAMS | Done
30 | COMLNR | RSN | Consumption Screen | CAMS | Done
30 | COMLNR | MSB | Consumption Screen | CAMS | Done
30 | COMLNR | ADT | Consumption Screen | CAMS | Done
30 | COMLNR | PCR | Consumption Screen | CAMS | Done
30 | COMLNR | RPR | Consumption Screen | CAMS | Done
30 | COMLNR | RGR | Consumption Screen | CAMS | Done