## Parevi
Sr No | Description | Tools & Technology | Location | Status | Target Date | Remarks
1 | Production Module Clarksville | CAMS/NOW | USA | Under Testing | 2023-06-23 | Working on Waste Screen for Gross WT,Net WT
2 | USA Import Errors | NOW
3 | FBG COA report | NOW | IND | Done | 2023-06-06 | Changes done and sent to user for confirmation.
4 | Project and Zone Location update for LNR Company 30 | CAMS | USA | Under Observation | 2023-06-09 | Harsh bhai will Confirm.
5 | Pendergrass Label Match with athens | CAMS | USA | Under Testing | 2023-06-07 | Parevi is testing.
6 | Pendergrass GI taken wrong Primary qty.(negative qty) | CAMS | USA | Ready to keep in LIVE | 2023-06-01 | Changes in QA is done.
7 | WLR spool update transaction taking kg in primary qty | CAMS | USA - Comm | Done | 2023-06-06 | Harsh bhai will Confirm.
8 | PET Production : Increase in Validation while doing Production Entry | CAMS | IND | Done | 2023-06-01 | PET Production Team will confirm.
9 | vTiger <-> Power Bi Connection | vTiger | IND,USA | In Process | 2023-06-10
10 | Yarn Container went in error due to lot update and wasn't updated in CAMs Balance so cleared all error and change in code in CAMs | CAMS/NOW | IND | Done | 2023-06-02
11 | Purchase Screen in Athens | CAMs QA | USA | Done | 2023-05-27 | Kept in LIVE, Lalit bhai is giving training to Nirja.
12 | Consumption Screeen in Athens | CAMs QA | USA | Done | 2023-05-27 | Kept in LIVE, Lalit bhai is giving training to Nirja.

## Vrushali
Sr No | Description | Tools & Technology | Location | Status | Target Date
1 | PET Waste screen | CAMS | IND | Under Testing | 2023-06-02
2 | FBG Roll & Pallet label as per customer PO | CAMS | IND | Done | 2023-05-30
3 | Production Module Clarksville | CAMS/NOW | USA | In Process
4 | WaitWhile Monitoring | IND
5 | INDIA Import Errors | NOW
6 | Reports - Jupiter - Element Labels | NOW | IND | Under Testing | 2023-06-09
7 | Reports - Jupiter- CoC | NOW | IND | In Process | 2023-06-12
8 | Reports - Jupiter- Traceability | NOW | IND | Entered | 2023-06-13

## Dipak
Sr No | Description | Tools & Technology | Status | Target Date | Remarks
1 | RUNNING VS EDGE TRIM WASTE Report - Woven | PowerBi | Hold |  | Ushaben will talk to Ashish bhai for this
2 | Division Wise Sales Export Report for all business | PowerBi | Done | 2023-06-02 | User will request more data soon
3 | Order Confirmation Report - Fiberglass | PowerBi | Entered | 2023-06-09
4 | Bags Order Summary Report | PowerBi | Done | 2023-06-09
5 | Non Woven Budget Tracker report | PowerBi | Working | 2023-06-09 | Working on some technical issues + manual entry issue
6 | Woven & Fiber Budget Reports | PowerBi | On Hold | - | Completed - but need to talk to user for report format
7 | Fiberglass Budget Report | PowerBi | Done | 2023-06-09
8 | Machine wise Fiberglass Production | PowerBi | Entered | 2023-06-13
Work: | Working on creation of power bi reports (Business Wise) with Aashni Team.
Working on technical issues of some existing power bi reports.
Meeting and Discussion with Aashni Team Members to get reports converted in PBI.

## Hitesh Maurya
Sr No | Description | Tools & Technology | Target Date | Status | Remarks
1 | Understand Work flow - Production & Consumption | Test Datatex - Com-100 | 2023-06-09 | Done
2 | Understand Database, Tables and Fields | DB Visualizer | 2023-06-09 | Done | Understood the Structure of the Tables and how it is used.
3 | Perform Queries related Production & Consumption | DB Visualizer | 2023-06-09 | Done | Non woven, fiber ,Fiber Glass , Woven
4 | I-net Report training | I-Net Designer | 2023-06-30
5 | Check reports of NOW Related Production | I-Net Designer | 2023-06-30
6 | Understand the Relation between tables | DB Visualizer | 2023-06-12
7 | Using of Formula & Condition for Reports | I-Net Designer | 2023-06-12
8 | Analyze the data from NOW to Database | Continuos Work
9 | Understand USA Fiber glass bussiness cycle (Sales,purchase,Production) | Datatex | 2023-06-19
10 | Understand USA Liner,WeldingRod bussiness cycle (Sales,purchase,Production) | Datatex | 2023-06-19
11 | Reading Documents Module wise | Continuos Work
Note: | I will go step by step with above mentioned task.
Also will communicate with Mundra team.
Plan a Plant Visit to Mundra to Understand Floor Operations

## Manish
Sr No | Description | Tools & Technology | Target Date | status
1 | Visit the plant and learn all the process of manufacturing ,raw materials used,storeroom data | Done
2 | Examine the properties of tables,schemas, and database objects | DB Visualizer | 2023-06-20 | in process
3 | analyze data from databases using SQL. | DB Visualizer | 2023-06-24
4 | Report creation | I-net | 2023-06-25 | in process
5 | Report layout design | I-net | 2023-06-25
6 | Read the documentation of the i-net-designer | I-net | 2023-06-30
9 | Analyze all the module of now | Continuos Work | 2023-06-08
10 | Using of Formula & Condition for Reports | i-net | 2023-06-20
11 | Make the production order production demand for the fiber glass | NOW (QA) |  | in process
12 | Quality Control (visit the quality lab learn about how non woven and fiber glass report submission | NOW(QA) |  | in process